## ProjectSchedule
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
First Phase
References and State of the art investigation | bar: Sep
Compare, test and choose the microcontroller | bar: Oct to Nov
Brief investigation on Neural Networks | bar: Nov to Dec
Design a first proposal of architecture | bar: Nov to Dec
Write Report | bar: Nov to Jan
Second Phase
Neural Network experiments | bar: Feb to Mar
Collect data | bar: Mar; Jun
Train Model | bar: Apr; Jul
Test Model | bar: May; Aug
Optimize Model | bar: Aug to Sep
Write Final Report | bar: May to Sep